Salem Alhabshi

Event Safety and Security Planning

Professor Raymond Martinez

11 Oct 24

Incident Action Plan (IAP) for Rock Palooza

Event Overview:

- Event Name: Rock Palooza

- Dates: February 15 & 16, 2025

- Location: Bayfront Park, Downtown Miami

- Event Hours:

  - Saturday: 4 PM - 12 AM

  - Sunday: 12 PM - 11 PM

- Expected Attendance: 15,000 attendees each day

- Ages: All ages

- Stages: 3 stages (Main Stage, Acoustic Stage, Emerging Artists Stage)

- Alcohol Sales: Yes (with strict monitoring)

1. Objectives

- Safety and Security:

  - We will maintain a secure environment for all participants.

  - We will prevent unauthorized access to restricted areas.

- Effective Communication:

  - We will ensure seamless communication among all staff and emergency services.

  - And provide clear information to attendees regarding safety protocols.

- Emergency Response:

  - We will be prepared for potential medical emergencies, weather-related issues, and security incidents.

  - And also will establish clear evacuation procedures.

- Crowd Management:

  - Ensuring effective crowd control to enhance attendee experience.

  - Monitor alcohol consumption to ensure responsible service.

  - Lost child / lost parents.

2. Organization and Staffing

- Event Command Structure:

  - Event Director

  - Operations Section Chief

  - Safety Officer

  - Public Information Officer (PIO)

  - Security Manager

  - Medical Services Coordinator

  - Logistics Manager

- Staffing Plan:

  - Security Personnel: We will have trained security staff, including:

    - personnels at entry/exit points.

    - personnels monitoring crowd areas and stages.

  - Medical Personnel: first-aid responders on-site, including:

    - EMTs on duty.

    - paramedics with an ambulance stationed on-site.

  - Volunteer Staff: volunteers for information and assistance, assigned specific zones within the venue.

3. Communication Plan

- Communication Tools:

  - Two-way radios for all key personnel to ensure immediate communication.

  - Phones: we will have personnels exchange phone numbers and named so they can contact one another by phone if necessary.

  - Mobile app for attendees to access event information, including schedules, maps, and emergency contacts. It will also be used to send emergency notifications.

  - Public address system for real-time announcements and emergency notifications.

- Emergency Contact List:

  - Local emergency services (fire, police, EMS) and their direct contact numbers.

  - Key event personnel contact information, including backup contacts.

4. Crowd Management

- Entry and Exit Points:

  - Designated entry points with ticket scanning and security checks (no weapon or anything that could be used as a weapon, and no big bags allowed like backpack or bigger).

  - Clearly marked exits with sufficient signage for emergency evacuation.

- Crowd Control Measures:

  - Use of barriers to manage crowd flow and prevent congestion.

  - Trained staff positioned throughout the venue to guide attendees and manage behavior.

- Monitoring Capacity:

  - On-site staff to continuously monitor attendance and manage crowd density.

- Children:

  - Lost child: contacting all security and tell them that there is a lost child. First thing to do is stopping anyone from exiting the event without ensuring that they do not have the missing child. Then we would describe hoe the child looks to all security guards to help finding them.

  - Lost parents: we will train employees on how to keep the child and calm them. We then will announce that we have a lost child who is looking for their parents.

5. Emergency Response Plan

- Medical Emergencies:

  - We will have first aid tents located at strategic locations, with clear signage and accessibility.

  - We will organize with local authorities for raped response protocols for any medical incidents, including immediate contact with EMS.

- Severe Weather Plan:

  - Utilize weather monitoring systems to track conditions.

  - Be ready to cancel the event or push the date if the weather condition was looking bad enough.

  - Communicate with attendees regarding evacuation plan if severe weather arises during the events.

- Evacuation Procedures:

  - Clear maps distributed to staff and posted throughout the venue showing evacuation routes.

  - Trained personnel at each exit to assist in orderly evacuation if necessary.

6. Alcohol Management

- Alcohol Sales Procedures:

  - Mandatory ID checks at all points of alcohol sale, we will not serve any one under 21. Those who get their IDs checked will get a wristband so they will not need to show their IDs anymore. Each day we will have a new color for wristbands.

  - Limit on the number of drinks purchased per transaction to promote responsible consumption.

- Monitoring Consumption:

  - Security personnel trained to identify signs of intoxication and intervene as necessary.

  - We will have free water stations throughout the venue to help keeping people hydrated.

7. Logistics

- Vendor Management:

  - Secure necessary permits for food and beverage vendors; ensure they are compliant with health and safety regulations.

  - All vendors to have a designated area with sufficient space for operations.

- Waste Management:

  - Placement of waste and recycling bins throughout the venue, with clear signage for disposal. We will also fix the bins in the ground so they cannot be moved so individual cannot flip it and stand on it.

  - We will have regular waste collection schedules to maintain cleanliness.

- Transportation and Parking:

  - Designate parking areas for attendees with a capacity for at least 5,000 vehicles, As well as, having people park on street parking around the event if needed and organize that with local authorities.

  - Having drop and pickup areas for transportation that are a little away from each other to prevent congestion.